## Go live checklist
Website Project Management Template
Project name |  | Client |  | Target launch date
Progress
Overall completion |  | 0% | 0/88 done
Initial Client Contacts |  | 0/3 | 0%
Pre Design |  | 0/13 | 0%
Design |  | 0/13 | 0%
Development |  | 0/14 | 0%
Sanity check |  | 0/18 | 0%
Browser & responsiveness |  | 0/4 | 0%
SEO essentials |  | 0/3 | 0%
Artificial Intelligence Optimisation (AIO) essentials |  | 0/3 | 0%
Go live steps |  | 0/8 | 0%
Google setup |  | 0/3 | 0%
Follow up |  | 0/6 | 0%
Done | Task | Who | When | Notes
Initial Client Contact
FALSE | Meet with the client and define the scope of the project |  | 2026-01-01
FALSE | Create a quote and proposal and send to client (make sure to include Rocketspark costs) |  | 2026-01-01
FALSE | Quote accepted |  | 2026-01-01
Pre Design
FALSE | Set project up in time tracking software |  | 2026-01-01
FALSE | Send deposit invoice (50%) |  | 2026-01-01
FALSE | Set up assets folder for the client in Google Drive |  | 2026-01-01
FALSE | Screenshot their existing website |  | 2026-01-01
FALSE | Set the website launch date - plan key milestones back from here |  | 2026-01-01
FALSE | When deposit received, notify customer of timeframes |  | 2026-01-01
FALSE | Prepare the strategy |  | 2026-01-01
FALSE | Meet with the client to discuss the strategy |  | 2026-01-01
FALSE | Take the creative brief |  | 2026-01-01
FALSE | Produce and get sign off for the reverse brief |  | 2026-01-01
FALSE | Share project file with client, including getting started requirements |  | 2026-01-01
FALSE | Make notes of the domain and email situation |  | 2026-01-01
FALSE | Get any required widgets, acccount passwords etc |  | 2026-01-01
Design
FALSE | Create the moodboard and present to client |  | 2026-01-01
FALSE | Wait for homepage content |  | 2026-01-01
FALSE | Create initial homepage concept |  | 2026-01-01
FALSE | Present concept to client |  | 2026-01-01
FALSE | Get Initial feedback from client |  | 2026-01-01
FALSE | Revise design based on feedback |  | 2026-01-01
FALSE | Present first revision to customer |  | 2026-01-01
FALSE | Get second round of revision from client |  | 2026-01-01
FALSE | Second round of design revision |  | 2026-01-01
FALSE | Get sign off from customer to build design |  | 2026-01-01
FALSE | Add photos and design assets into Dropbox |  | 2026-01-01
FALSE | Follow up content if not received |  | 2026-01-01
FALSE | 25% (1st) Invoice for design completion |  | 2026-01-01
Development
FALSE | Create draft site in Design Studio |  | 2026-01-01
FALSE | Make sure the email on Rocketspark account is correct and not a dummy email address. |  | 2026-01-01
FALSE | Setup favicon |  | 2026-01-01
FALSE | Build Desktop Homepage |  | 2026-01-01
FALSE | Tweak Mobile Homepage |  | 2026-01-01
FALSE | Build out all pages on desktop |  | 2026-01-01
FALSE | Tweak all pages on mobile |  | 2026-01-01
FALSE | Check desktop build looks good |  | 2026-01-01
FALSE | Check responsive versions looks good |  | 2026-01-01
FALSE | Check that content is SEO rich |  | 2026-01-01
FALSE | Send website to client to view website |  | 2026-01-01
FALSE | Client feedback |  | 2026-01-01
FALSE | Additional changes |  | 2026-01-01
FALSE | Get client sign off on build |  | 2026-01-01
Sanity Check
FALSE | No placeholder or dummy content anywhere on the site |  | 2026-01-01
FALSE | No broken internal links or buttons |  | 2026-01-01
FALSE | Slideshow links all working correctly |  | 2026-01-01
FALSE | No large unexplained white spaces or inconsistent spacing |  | 2026-01-01
FALSE | Quick scan for obvious typos |  | 2026-01-01
FALSE | Easy to navigate the site wearing a "visitor" hat |  | 2026-01-01
FALSE | All pages feel as polished and designed as the homepage |  | 2026-01-01
FALSE | Consistent styling throughout the entire site |  | 2026-01-01
FALSE | All contact details are correct |  | 2026-01-01
FALSE | All forms submitting to the correct email addresses |  | 2026-01-01
FALSE | Columns in stacks generally balance in height |  | 2026-01-01
FALSE | No blurry or low-resolution images |  | 2026-01-01
FALSE | All visible pages have content and look complete |  | 2026-01-01
FALSE | No dummy or placeholder blog posts |  | 2026-01-01
FALSE | Blog fonts and headings match the rest of the site styling |  | 2026-01-01
FALSE | All blocks styled, even those not active at launch (buttons, blog posts, etc.) |  | 2026-01-01
FALSE | Homepage text mentions the company name |  | 2026-01-01
FALSE | Homepage content includes main keywords |  | 2026-01-01
Browser & Responsiveness
FALSE | Check across different screen sizes (large monitor, laptop) |  | 2026-01-01
FALSE | Full mobile preview and refine if needed |  | 2026-01-01
FALSE | Cookie/privacy policy page looks correct |  | 2026-01-01
FALSE | Terms and conditions page looks correct |  | 2026-01-01
SEO Essentials
FALSE | Keywords on each page, title and description tags set |  | 2026-01-01
FALSE | If replacing existing site, match existing title and description tags |  | 2026-01-01
FALSE | If replacing existing site, set up URL redirects before go live |  | 2026-01-01
Artificial Intelligence Optimisation (AIO) Essentials
FALSE | Optimise for LLMs (ChatGPT, etc.) with AI Overview optimisation |  | 2026-01-01
FALSE | Add FAQ accordions to support AI Overview results |  | 2026-01-01
FALSE | Implement site-wide schema markup |  | 2026-01-01
🚀 Go Live Steps
FALSE | Send completion invoice (final 25%) |  | 2026-01-01
FALSE | Go live once completion payment is received |  | 2026-01-01
FALSE | Send client info on how to upgrade their plan |  | 2026-01-01
FALSE | Register or transfer domain (note domain status in Notes) |  | 2026-01-01
FALSE | If transferring, confirm email migration plan (POP, IMAP, or webmail) |  | 2026-01-01
FALSE | If webmail/POP, explain existing inbox can't transfer to Rocketspark |  | 2026-01-01
FALSE | Set up new email accounts or migrate to Rocketspark |  | 2026-01-01
FALSE | Confirm email hosting status |  | 2026-01-01
Google Setup
FALSE | Link Google Analytics |  | 2026-01-01
FALSE | Set up Search Console and submit sitemap |  | 2026-01-01
FALSE | Create or claim Google Business Profile |  | 2026-01-01
Follow Up
FALSE | Get client permission to feature site in your marketing |  | 2026-01-01
FALSE | Schedule a time to demo the Rocketspark CMS to the client |  | 2026-01-01
FALSE | After 2 weeks: check SEO indexing and performance |  | 2026-01-01
FALSE | After 4 weeks: contact client to check satisfaction and review analytics |  | 2026-01-01
FALSE | Add to your portfolio (if the work is strong enough) |  | 2026-01-01
FALSE | Archive the project in your time tracking software |  | 2026-01-01
Made by Rocketspark 🩵 rocketspark.com

## Instructions
How to Use This Template
This checklist covers everything from kicking off the project through to post-launch follow-up. It's designed to be used as a Google Sheet so you can collaborate and track progress in real time.
What the Columns Are For
Done
Tick this when the task is complete. Drives the progress tracking at the top.
Task
The checklist item. Edit or add to these to suit your workflow.
Who
Add who is repsonsible for completing this task
When
Use this to set deadlines or record completion dates.
Notes
Free text for anything relevant: domain details, client preferences, links, follow-up reminders.
How Progress Tracking Works
The dashboard at the top of the checklist tab shows two things:
Overall completion
A percentage and count (e.g. 12/88 done) across all items.
Per-section progress
Each of the sections shows its own fraction and percentage, so you can see at a glance which areas still need attention.
Tips
- We've included useful links to our help centre on some of tasks. Check them out!
- Make a copy of this sheet for each new project (File > Make a copy).
- If you add or remove checklist rows, update the COUNTIF formula ranges in the progress section to match.
- Use the Notes column liberally. Future-you will thank present-you.
Made by Rocketspark 🩵 · rocketspark.com